## Sheet1
		Notes:
		Qestions:	number of bugs is large: if more study is needed postpone?

Core: State Machine	Count:19	Link	Type	Status	Priority	Title	Type	Est (work day)	Action	Note
		https://bugreports.qt.io/browse/QTBUG-9380	Suggestion	Open	3	It would be useful if QStateMachine had a signal to notify about configuration changes	feature req	3	do it	would be nice and think its a basic thing to have
		https://bugreports.qt.io/browse/QTBUG-9842	Task	Open	4	Transitions with multiple target states: Missing documentation and runtime check	feature req/doc	2/1	decision needed	Verify that the premises are the case and decide how to proceed
		https://bugreports.qt.io/browse/QTBUG-9954	Suggestion	Open	3	Enable property un-assign for QtState	bugfix/feature req	3	do it	sound as a missing basic feature
		https://bugreports.qt.io/browse/QTBUG-10387	Bug	Open	3	Parallel child states are not "insulated" from each other.	bugfix/feature req	1	document if needed/close	just close this for now as this is the intended behavior
		https://bugreports.qt.io/browse/QTBUG-17861	Bug	Open	4	QState::assignProperty feature should take a restorePolicy	feature req	3	should be a suggestion	later
		https://bugreports.qt.io/browse/QTBUG-19358	Bug	Open	4	QStateMachine does not support exceptions	bug	2	raise prio and do it/decide	should continue? decide
		https://bugreports.qt.io/browse/QTBUG-20158	Bug	Open	2	QStateMachine docs do not note that custom Events are not allowed	bug	5	more study needed -> postpone
		https://bugreports.qt.io/browse/QTBUG-28946	Bug	Reported	3	QStateMachine: adding parallel states to running machine fails	bug/intended	3	study if this is intended	study needed -> postpone?
		https://bugreports.qt.io/browse/QTBUG-38649	Bug	Reported	3	QState entered/exited signals are not emmited after a history state	bug	2	need more study	Don't know how history state works
		https://bugreports.qt.io/browse/QTBUG-39799	Bug	Open	3	QState::addTransition(sender, signal, target) should accept null as target	bug	2	study if this is intended and why	study needed -> postpone?
		https://bugreports.qt.io/browse/QTBUG-40219	Bug	Open	3	Fix for QTBUG-30049 regressed the fix for QTBUG-25958 (history issue)	bug	5?	need more study	study needed -> postpone?
		https://bugreports.qt.io/browse/QTBUG-45033	Bug	Open	2	Non deteministic ordering of execution with parallel states	bug	5	do it	state machine should be deterministic
		https://bugreports.qt.io/browse/QTBUG-45111	Suggestion	Reported	4	State Machine Framework: make UnconditionalTransition public	feature req	3	study if this is useful/not agains specs	study needed -> postpone?
		https://bugreports.qt.io/browse/QTBUG-46236	Bug	Reported	3	REG 4.8.6->5.4.1 QHistoryState - History not restored on self-transition to containing state	bug?/feature?	3	study if this a bug or intended	study needed -> postpone?
		https://bugreports.qt.io/browse/QTBUG-46772	Bug	Reported	3	QState does not support setting the initial state to a "deep" state	not valid probably	1	study if this is what the specs say
		https://bugreports.qt.io/browse/QTBUG-52220	Bug	Reported	3	qtbase fails to build with --no-feature-PROPERTIES	build issue	2	check what this is and if its still valid
		https://bugreports.qt.io/browse/QTBUG-54908	Suggestion	Reported	3	Allow processing of unconsumed external events	feature req	5	unclear if this is needed -> postpone
		https://bugreports.qt.io/browse/QTBUG-57835	Bug	Closed	3	QState addTransition doesn't wotk in c++/clr environment	bug?	3	unclear if this is needed -> postpone
		https://bugreports.qt.io/browse/QTBUG-66070	Suggestion	Open	3	Add a signal/virtual protected that is emitted/called when a state in the state machine is entered	feature req	2	do it

		https://bugreports.qt.io/browse/QTBUG-91375	Task	In Progress	2	Qt StateMachine: add QProperty binding support where beneficial	porting	10		core state machine task

XML: SCXML	Count: 43
		https://bugreports.qt.io/browse/QTBUG-58564	Bug	Reported	2	Public API for invoked state machines missing	feature req	3	unclear if this is needed -> postpone
		https://bugreports.qt.io/browse/QTBUG-60045	Bug	Closed/fixed	2	SCXML examples fail to compile with -no-gui	bug	1	probably fixed by making ecamscript a dll	verify
		https://bugreports.qt.io/browse/QTBUG-63336	Bug	Closed/fixed	2	When history state is used in scxml, some state ids are wrong	bug	3	fix
		https://bugreports.qt.io/browse/QTBUG-66506	Task	Open	3	Add more optional convenience features for code generated from SCXML	feature req	7	postpone	doesnt seem essential
		https://bugreports.qt.io/browse/QTBUG-66507	Task	Open	3	Add schema validation for scxml documents	feature req	10	needs more study how big of a task this would be
		https://bugreports.qt.io/browse/QTBUG-66509	Task	Open	3	Add support for further parts of the SCXML standard	feature req	10+	needs more study for details	postpone
		https://bugreports.qt.io/browse/QTBUG-66598	Bug	Reported	2	When a history state is included inside a parent state then it is excluded from the generated code for the state machine	bug	5	fix
		https://bugreports.qt.io/browse/QTBUG-70261	User Story	Withdrawn	2	Rewrite QStateMachine and QML state machine on top of QtScxml	rewrite	50	-
		https://bugreports.qt.io/browse/QTBUG-71864	Bug	Reported	3	SCXML <donedata> <param>s do not end up in the resulting event's data	bug	5	more study needed for exact work amount
		https://bugreports.qt.io/browse/QTBUG-75096	Bug	Reported	2	Cannot compile Full Namespace Scxml	bug	3	fix	no essential tho probs
		https://bugreports.qt.io/browse/QTBUG-76091	Bug	Closed/fixed	1	QScxmlStateMachine crashes when transitioning to a previously never used history state.	bug	3	fix
		https://bugreports.qt.io/browse/QTBUG-76332	Suggestion	Reported	3	Add guard predicate to QSignalTransition	feature req	5	postpone	not essential
		https://bugreports.qt.io/browse/QTBUG-78689	Suggestion	Reported	3	extend SCXML to support BPMN 2.0	feature req	?	unclear how big of task this would be	probs unfeasibly big
		https://bugreports.qt.io/browse/QTBUG-80262	Bug	Reported	3	SCXML StateMachine state properties get incorrect values if History is used	bug	7	fix
		https://bugreports.qt.io/browse/QTBUG-82141	Suggestion	Reported	3	Be able to have an event automatically propagate up to a parent state machine if it is not handled by the child state machine	feature req	3
		https://bugreports.qt.io/browse/QTBUG-82460	User Story	Open/in progress	2	Document qt5_add_statecharts CMake API for Scxml Module	doc	2	Juha checking what to do with the bug (fix to Qt6 vs won't fix at all)
		https://bugreports.qt.io/browse/QTBUG-82625	Bug	Reported	3	Hierarchical state machines transitions not handled as expected	feature req	3
		https://bugreports.qt.io/browse/QTBUG-82625	Suggestion	Reported	2	QtScXML module does not export dependency on QML	bug	2
		https://bugreports.qt.io/browse/QTBUG-83487	Suggestion	Reported	3	Make it possible to check possible transitions for each state in a QScxmlStateMachine.	feature req	3
		https://bugreports.qt.io/browse/QTBUG-84387	Bug	Reported	3	qt5_add_statecharts CMake function not setting SKIP_AUTOMOC flag correctly	bug	2	verify
		https://bugreports.qt.io/browse/QTBUG-86626	Bug	Reported	2	Adding History state breaks state chart	bug	3		has fix proposal and detailed desc
		https://bugreports.qt.io/browse/QTBUG-87696	Bug	Reported	3	QStateMachine: Error States are insufficiently explained	doc	2
		https://bugreports.qt.io/browse/QTBUG-88611	Epic	In Progress	2	Migrate Qt ScXML/QStateMachine to Qt 6	epic
		https://bugreports.qt.io/browse/QTBUG-88778	Bug	Reported	2	SCXML state machine start and stop have errors in QML	bug	3
		https://bugreports.qt.io/browse/QTBUG-89285	Bug	Reported	2	Document changes to State Machine Framework in Core Migraion Guide	doc	1
		https://bugreports.qt.io/browse/QTBUG-89504	Epic	In Progress	1	Module Migration for Qt 6.1	epic
		https://bugreports.qt.io/browse/QTBUG-89830	Task	In Progress	2	Qt SCXML: Synchronize MOC code with qtbase and create patch file		3
		https://bugreports.qt.io/browse/QTBUG-89836	Task	Reported	2	Qt SCXML: Improve, verifiy and/or fix tests	verification	3
		https://bugreports.qt.io/browse/QTBUG-89837	User Story	Open	2	Qt SCXML: Rename the module to a more general name, e.g. qtstatemachine	reorg	5
		https://bugreports.qt.io/browse/QTBUG-89838	User Story	Open	3	Qt SCXML: Implement new features	dev	10+
		https://bugreports.qt.io/browse/QTBUG-89845	Task	In Progress	2	Qt SCXML: Bug triaging/ fixing	mangement	3
		https://bugreports.qt.io/browse/QTBUG-89847	Task	Reported	2	Qt SCXML: Unite component XML: SCXML and Core: State Machine	reorg	5
		https://bugreports.qt.io/browse/QTBUG-89895	Task	In Progress	2	Qt SCXML: add QProperty binding support where beneficial	porting	15
		https://bugreports.qt.io/browse/QTBUG-90544	Bug	Reported	2	SCXML nested invoke src is not resolved properly	bug	5
		https://bugreports.qt.io/browse/QTBUG-90720	Bug	Reported	2	[SCXML] Fail to parse 'delay' time with floating point values (W3C Test175)	bug	5
		https://bugreports.qt.io/browse/QTBUG-90721	Bug	Reported	2	[SCXML] Events with target '#_internal' are not put to the internal queue (W3C Test189)	bug	5
		https://bugreports.qt.io/browse/QTBUG-90722	Bug	Reported	2	[SCXML] Events with target '#_scxml_sessionid' are not put to the external queue (W3C Test190)	bug	5
		https://bugreports.qt.io/browse/QTBUG-90742	Bug	Reported	2	[SCXML] Scion scxml-test-framework is not updated to the latest W3C SCXML Standard	maintenance	5
		https://bugreports.qt.io/browse/QTBUG-90787	Bug	Closed/fixed	1	CMake Error at /home/qt/work/install/lib/cmake/Qt6Qml/Qt6QmlMacros.cmake	build issue	3	verify	might be fixed already
		https://bugreports.qt.io/browse/QTBUG-90909	Task	Reported	2	Enable QtScxml per-module builds with Conan	porting	3		postponed to 6.2, unsolvable at the moment (larger topic)
		https://bugreports.qt.io/browse/QTBUG-91057	Suggestion	Reported	3	Add a means to get the QScxmlStateMachine for the invoked service	feature req	3
		https://bugreports.qt.io/browse/QTBUG-91151	Task	Reported	2	Verify Qt 6 SCXML module's interoperability with Qt Creator's SCXML editor	porting	3
		https://bugreports.qt.io/browse/QTBUG-91358	Bug	Need More Info	2	Unable to build QtScxml Add-On with Conan, Qt6.1.0 alpha&beta1, macOS-clang-10.14-x64_iOS	build issue	3		conan
		https://bugreports.qt.io/browse/QTBUG-92041	Suggestion	Reported	4	QT SCXML: Possible improvement tasks for examples	example improvements	5